## Final Sheet
HPCL Rajasthan Refinery PO Summary Details during Feb-21 to March-2023
Sl no | Procurement Month | Tender no | Item / Nature of work | Mode of tender enquiry | Date of Publication of NIT | Due date of the tender | Nos. of the parties qualified after TE | Nos. of the parties not qualified after TE | Whether contract awarded to L1 bidder | LOA No | Date | PO No | PO Date | Vendor | Contract value in Crores (Inclusive of GST) (INR)
1 | 2021-04-01 | GEM/2021/B/1115630 | Providing Security Services (DGR Approved) at Site | thru GeM | 2021-03-20 | 2021-03-30 | 4 | 2 | YES | GEMC-511687718182616 | 2021-04-21 |  |  | RAJASTHAN EX-SERVICEMEN CORPORATION LIMITED | 18.8537
2 | 2021-08-01 | AKR/B224-121-PM-T-7306/2015 | EPCC-06 Package – Sulphur Recovery Block | Public-Global | 2021-02-19 | 2021-04-26 | 4 |  | YES | HRRL/LOA/2021/21 | 2021-08-23 |  |  | Megha Engineering & Infrastructures Limited | 1619.7313
3 |  | AKR/B224-105-PM-T-7302/2014 | EPCC-02 Package – MS BLOCK CONSISTING OF NAPHTHA HYDRO TREATING UNIT (NHT), ISOMERIZATION UNIT (ISOM) AND PFCC GASOLINE HYDRO TREATING UNIT | Public-Global | 2021-02-19 | 2021-05-05 | 6 | NIL | YES | HRRL/LOA/2021/22 | 2021-08-27 |  |  | Technip India Limited | 1543.5061
4 | 2021-09-01 | DC/B224-323-MA-T-6002/3002 | Double Wall Tanks (DWST) including dyke and facilities within dyke at Rajasthan Refinery Complex at Pachpadra (PACKAGE-7, Part A) | Public-Global | 2019-11-15 | 2020-12-04 | 2 | 1 | YES | HRRL/LOA/2021/24 | 2021-09-06 |  |  | CHEMIE TECH DMCC | 663.4155
5 |  | DC/B224-323-MA-T-6002/3002 | Mounded Bullets including dyke and facilities within dyke at Rajasthan Refinery Complex at Pachpadra (PACKAGE-7, Part B) | Public-Global | 2019-11-15 | 2020-12-04 | 2 | 1 | YES | HRRL/LOA/2021/29 | 2021-09-20 |  |  | VIJAY TANKS & VESSELS PVT. LTD. | 461.9598
6 |  | DC/B224-000-FP-T-0480/026 | Fire Detection & Alarm System (Package-12) | Public | 2021-01-01 | 2021-03-04 | 4 | 1 | YES | HRRL/LOA/2021/30 | 2021-09-20 |  |  | Sterling and Wilson Private Limited | 14.4155
7 | 2021-11-01 | SM/B224-030-EP-T-9500/1020 | EPCC-20 Package for Imported Crude Oil Pipeline from COT Mundra to Barmer Refinery | Public-Global | 2020-11-23 | 2021-03-04 |  |  | YES | HRRL/LOA/2021/38 | 2021-11-03 |  |  | Megha Engineering & Infrastructures Ltd. | 2082.1348
8 |  | DC/B224-020-EP-T-9880/026 | Crude Oil Terminal (COT) and associated facilities at Mundra, Gujarat (EPCC-11) | Public-Global | 2021-01-16 | 2021-03-15 | 2 | 2 | YES | HRRL/LOA/2021/39 | 2021-11-13 |  |  | CHEMIE TECH DMCC | 1350.8758
9 |  | AKR/B224-137-PM-T-7309/2012 | EPCC-09 Package - Polypropylene Unit & Associated Conveying and Bagging System and Butene-1 Unit | Public-Global | 2021-02-17 | 2021-04-28 | 3 | NIL | YES | HRRL/LOA/2021/40 | 2021-11-13 |  |  | Megha Engineering & Infrastructures Ltd | 3423.793
10 |  | AKR/B224-136-PM-T-7308/2016 | EPCC-08 Package – LLDPE/HDPE (Swing) Unit & Associated Conveying and Bagging System | Public-Global | 2021-02-24 | 2021-04-30 | 4 | NIL | YES | HRRL/LOA/2021/41 | 2021-11-13 |  |  | Megha Engineering & Infrastructures Ltd | 3636.3006
11 |  | DC/B224-323-MA-T-6004/3010 | CRUDE STORAGE TANKS INCLUDING TANK PADS AND ASSOCIATED CIVIL WORKS (PACKAGE-5) | Public-Global | 2020-12-30 | 2021-02-17 | 2 | 5 | YES | HRRL/LOA/2021/42 | 2021-11-13 |  |  | BRIDGE AND ROOF COMPANY (INDIA) LIMITED | 341.0672
12 |  | DC/B224-323-MA-T-6005/3011 | Part : A of Intermediate & Product Storage Tanks Including Tank Pads and Associated Civil Works (PACKAGE-6) | Public-Global | 2020-12-30 | 2021-02-18 | 2 | 3 | YES | HRRL/LOA/2021/43 | 2021-11-13 |  |  | CHEMIE TECH DMCC | 488.756
13 |  | DC/B224-323-MA-T-6005/3011 | Part – B of Intermediate & Product Storage Tanks Including Tank Pads and Associated Civil Works (PACKAGE-6) | Public-Global | 2020-12-30 | 2021-02-18 | 2 | 3 | YES | HRRL/LOA/2021/44 | 2021-11-13 |  |  | BRIDGE AND ROOF COMPANY (INDIA) LIMITED | 526.3331
14 |  | DC/B224-000-CP-T-8102/29 | Non Plant Buildings (Package – 22) | Public | 2021-05-13 | 2021-07-08 | 6 | 1 | YES | HRRL/LOA/2021/45 | 2021-11-13 |  |  | Dee Vee Projects Ltd. | 310.0731
15 |  | DC/B224-324-CV-T-8010/25 | Product Ware House and Workshop (Package-14) | Public | 2020-11-02 | 2020-12-14 | 7 | 1 | YES | HRRL/LOA/2021/46 | 2021-11-13 |  |  | Montecarlo Limited | 392.94
16 |  | DC/B224-323-MA-T-6002/3002 | Spheres including dyke and facilities within dyke at Rajasthan Refinery Complex at Pachpadra (PACKAGE-7, Part C) | Public-Global | 2021-11-15 | 2020-12-04 | 3 | 1 | YES | HRRL/LOA/2021/47 | 2021-11-13 |  |  | SHARP TANKS & STRUCTURALS (P) LTD. | 106.0921
17 |  | DC/B224-000-EK-T-0470/030 | Plant Communication System (Package-11) | Public | 2021-05-19 | 2021-07-22 | 2 | NIL | YES | HRRL/LOA/2021/48 | 2021-11-13 |  |  | Dee-Em Systems | 22.3846
18 |  | DC/B224-510-MD-T-4530/3013 | Demountable Flare System Package (Package-4) | Public-Global | 2021-03-24 | 2021-05-21 | 2 | 2 | YES | HRRL/LOA/2021/49 | 2021-11-15 |  |  | Airoil Flaregas Private Limited (Prime Member) & S.K.B. Builders India Limited (Member), | 363.8884
19 |  | DC/B224-000-AZ-MR-8100/6 | STORAGE RACKING SYSTEM FOR PEB WAREHOUSE | Public | 2021-05-04 | 2021-06-22 | 2 | 2 | YES | HRRL/LOA/2021/53 | 2021-11-26 |  |  | Godrej & Boyce Mfg. Co. Ltd. | 23.836
20 | 2021-12-01 | DC/B224-000-CQ-T-8022/28 | BALANCE CIVIL WORKS for Rajasthan Refinery Project of HRRL | Public | 2021-06-21 | 2021-08-12 | 20 | 8 | YES | HRRL/LOA/2021/55 | 2021-12-14 |  |  | TAN SINGH CHOUHAN | 83.0061
22 | 2022-04-01 | DC/B224-511-PG-T-9517/3014 | Utility Boilers and Associated Systems (Package-9A) | Public-Global | 2021-10-21 | 2021-12-15 | 1 | 1 | YES | HRRL/LOA/2022/15 | 2022-04-12 |  |  | Thermax Limited | 617.081
23 | 2022-06-01 | DC/B224-000-EP-T-2662/033 | Ambient Air Quality Monitoring System (Package-13) | Public | 2021-12-31 | 2022-02-21 | 4 | NIL | YES | HRRL/LOA/2022/19 | 2022-06-14 |  |  | Analyser Instrument Co. Pvt. Ltd. | 5.6758
24 | 2022-07-01 | DC/B224-000-EP-T-2470/031 – Part-B) | SCADA & APPS System (Part-B) (Package-18) | Public |  |  |  |  | YES | HRRL/LOA/2022/25 | 2022-07-25 |  |  | ABB India Limited | 8.436
25 | 2022-08-01 | DC/B224-000-EP-T-2510/032 | Tank Farm Management System (Part-A) (Package-8) | Public-Domestic | 2021-11-15 | 2022-03-15 | 2 | 1 | YES | HRRL/LOA/2022/36 | 2022-08-29 |  |  | Honeywell Automation India Limited | 21.0464
26 | 2022-09-01 | DC/B224-000-EP-T-2510/032 | Blending Automation System (Part-B) (Package-8) | Public-Domestic | 2021-11-15 | 2022-03-15 | 1 | NIL | YES | HRRL/LOA/2022/40 | 2022-09-16 |  |  | Yokogawa India Limited | 36.8854
27 | 2022-10-01 | DC/B224-511-PG-T-9522/3017 | STG & ASSOCIATED SYSTEMS (PACKAGE-9B) | Public-Global | 2022-07-08 | 2022-08-22 | 2 | 1 | YES | HRRL/LOA/2022/44 | 2022-10-06 |  |  | Megha Engineering & Infrastructures Ltd. | 1529.28
28 |  | DC/B224-511-PG-T-9521/3018 | CFBC Boilers & Associated Systems (PACKAGE-10A) | Public-Global | 2022-07-08 | 2022-08-24 | 2 | 1 | YES | HRRL/LOA/2022/45 | 2022-10-06 |  |  | Megha Engineering & Infrastructures Ltd. | 2234.92
29 | 2022-12-01 | 22000030-HD-09373 | ERP Solution for HPCL Rajasthan Refinery Limited (HRRL) | Public | 2022-09-14 | 2022-11-15 | 1 | 2 | YES | HRRL/LOA/2022/52 | 2022-12-03 |  |  | ERNST & YOUNG LLP (EY) | 26.4602
30 | 2023-01-01 | 22000040-HB-09373 | Design and Construction of Senior Secondary School | Limited | 2022-11-30 | 2022-12-21 | 4 | 0 | YES | HRRL/LOA/2023/01 | 2023-01-09 |  |  | Tan Singh Chouhan | 9.8
31 | 2023-02-01 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
32 | 2023-03-01 | AS/B224-323-MA-TN-6006/3021 | Intermediate & Product Storage Tanks Including Tank Pads And Associated Civil Works | Public Tener | 2022-11-11 | 2022-12-16 | 4 | NA | Yes | HRRL/LOA/2023/06 | 2023-03-17 | NA | NA | Mahathi Infra Services Pvt. Ltd | 533.91
33 |  | AS/B224-020-EP-TN-9900/3022 | Crude Oil Terminal (COT) and associated facilities at Mundra, Gujarat (EPCC-11) | Public Tener | 2022-11-17 | 2023-01-03 | 3 | NA | Yes | HRRL/LOA/2023/07 | 2023-03-20 | NA | NA | AFCONS INFRASTRUCTURE LIMITED | 1340.59
34 |  | 22000044-HD-09373 | Construction of Hospital Building | Public Tener | 2023-01-24 | 2023-02-15 | 6 | 1 | Yes | HRRL/LOA/2023/09 | 2023-03-29 | NA | NA | Makers Buildtech | 9.58